## Hoja1
TASKS |  | modelID | en protopred? | STATUS[*] | [**]DESCRIPTORES | MODEL | setids [see info datas sheet] | Additional notes
Paralelización
Structural Clustering |  |  |  | ongoing
In vitro CACO2 hepatic metabolism, and CYP inhibition
| CACO2 |  | ProtoPRED- check
| CYP3a4-substrate | TK_CYP3A4sub |  | local: reimputed in linux server | [Enrique] server [217][all??] |  | CYP3A4_NO_outliers
| CYP2c9-subs | TK_CYP2C9sub |  | local: reimputed in linux server | [Enrique] server [217][all??] |  | CYP2C9
| CYP2c19-subs | TK_CYP2C19sub |  | local: reimputed in linux server | [Enrique] server [217][all??] |  | CYP2C19
| CYP1a2-sub | TK_CYP1A2sub |  | local: reimputed in linux server | [Enrique] server [217][all??] |  | CYP1A2
| CYP2d6-subs | TK_CYP2D6subs |  | local: reimputed in linux server | [Enrique] server [217][all??] |  | CYP2D6
| CYP3a4-inh | TK_CYP3A4inh |  | local: developed, but not reimputed | [Enrique] server [217][all??] |  | TK_CYP3A4inh_DeepPK
| CYP2c9-inh | TK_CYP2C9inh |  | local: developed, but not reimputed |  |  | TK_CYP2C9inh_DeepPK
| CYP2c19-inh | TK_CYP2C19inh |  | local: developed, but not reimputed |  |  | TK_CYP2C19inh_DeepPK
| CYP1a2-inh | TK_CYP1A2inh |  | ongoing: dataset preparado para calcular descriptores |  |  | TK_CYP1A2inh_DeepPK
| CYP2d6-inh | TK_CYP2D6inh |  | local: developed, but not reimputed | [Enrique] server [217][all??] |  | TK_CYP2D6inh_DeepPK
| Human liver microsome (HLM) stability | TK_HLM | ProtoPRED- check |  |  |  | TK_HLM_vnnADMET
| OATP1B1 inhibitor | TK_OATP1B1inh |  | local: developed, but not reimputed | Eva local [Eva][linux][all] | Eva | TK_OATP1B1inh_livertox
| OATP1B3 inhibitor | TK_OATP1B3inh |  | local: developed, but not reimputed | Eva local [Rita][linux][all] | Lauri | TK_OATP1B3inh_livertox
| BSEP inhibitor | TK_BSEPinh | ProtoPRED- check |  |  |  | [if needed]TK_BSEPinh_livertox
In vivo pharmacokinetics ADME (PK)
| Bioavailability 20% | TK_F20 | ProtoPRED- check
| Bioavailability 30% | TK_F30 | ProtoPRED- check
| Human Intestinal Absorption | TK_HIA | ProtoPRED- check
| P-glycoprotein inhibitor | TK_pgpinh | ProtoPRED- check
| P-glycoprotein substrate | TK_pgpsub | ProtoPRED- check |  |  |  | TK_Psub_Wang ,TK_Psub_Li, TK_Psub_livertox
| Skin permeability | TK_logKp | ProtoPRED- check
| Blood-brain barrier penetration | TK_BBB | ProtoPRED- check
| Plasma protein binding | TK_FU |  | ongoing: descriptores calculados | Carmen local [CarmenNuevo][linux][all] | Carmen | TK_FUB_Tonnelier ,TK_FUB_Yamazaki ,TK_FUB_Lombardo ,TK_FUB_Riley ,TK_FUB_Votano ,TK_FUB_cran ,TK_FUB_Zhu
| Volume of distribution | TK_VD |  | finished | [JL] server [217][all????]
Maximum tolerated dose toxicity (MTD) |  | TOX_MRDD |  | ongoing: descriptores calculados | Carmen local [CarmenViejo][linux] |  | TOX_MRDD_DeepPK
Inhibition of hERG, Nav 1.5, and Cav 1.2
| hERG, | TOX_hERGinh |  | ongoing: dataset preparado para calcular descriptores | Eva local [Eva][linux][no3D] |  | TOX_hERG_vnnADMET, hERG_inhibitor_chEMBL, DeepPK_herg_all
| Nav 1.5 | TOX_Nav15inh |  | ongoing: dataset preparado para calcular descriptores - problemas con algunas moléculas | Eva local [Rita][linux][all] |  | TOX_Nav15inh_ChEMBL, Nav_CtoxPred | Problems with descriptors calculation
| Cav 1.2 | TOX_Cav12inh |  | finished [two molecules have disapeared] | [Carmen] local [Lauri][linux][all] |  | TOX_Cav12inh_ChEMBL, TOX_Cav12inh_CtoxPred

## info datas
category | endpoint | setids | persona datos | persona processing | processed | source | original file - folder datasets_for_modelling | if needed, intermediate files folder | if needed, first processed file | processing method [***] | processed before?
TK | Psub | TK_Psub_Wang |  |  |  | Wang, Z., Chen, Y., Liang, H., Bender, A., Glen, R. C., & Yan, A. (2011). P-glycoprotein substrate models using support vector machines based on a comprehensive data set. Journal of chemical information and modeling, 51(6), 1447-1456. | pgp_testset.sdf¦pgp_trainingset.sdf |  |  |  | yes - ONTOX - Eva
TK | Psub | TK_Psub_Li |  |  |  | ADMET evaluation in drug discovery. 13. Development of in silico prediction models for P-glycoprotein substrates. 2014 Dan Li 1 , Lei Chen, Youyong Li, Sheng Tian, Huiyong Sun, Tingjun Hou. 2014 retrieved from VNN-ADMET server | Pgp_Substrates.csv |  |  |  | yes - ONTOX - Eva
TK | Psub | TK_Psub_livertox |  |  |  | Montanari_livetox_transporters -files in Data_Sheet_2 - | PgpTRANSP_training.sdf¦PgpTRANSP_test.sdf |  |  |  | No
TK | FU | TK_FUB_Tonnelier | Eva | Eva | yes | Tonnelier, A., Coecke, S., & Zaldívar, J. M. (2012). Screening of chemicals for human bioaccumulative potential with a physiologically based toxicokinetic model. Archives of Toxicology, 86, 393-403. | EVA |  | TK_FUB_Tonnelier.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_Yamazaki | Eva | Eva | yes | Yamazaki, K., & Kanaoka, M. (2004). Computational prediction of the plasma protein‐binding percent of diverse pharmaceutical compounds. Journal of Pharmaceutical Sciences, 93(6), 1480-1494. | EVA |  | TK_FUB_Yamazaki.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_Lombardo | Eva | Eva | yes | Lombardo, F., Obach, R. S., Shalaeva, M. Y., & Gao, F. (2002). Prediction of volume of distribution values in humans for neutral and basic drugs using physicochemical measurements and plasma protein binding data. Journal of Medicinal Chemistry, 45(13), 2867-2876. | EVA |  | TK_FUB_Lombardo.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_Riley | Eva | Eva | yes | Riley, R. J., McGinnity, D. F., & Austin, R. P. (2005). A unified model for predicting human hepatic, metabolic clearance from in vitro intrinsic clearance data in hepatocytes and microsomes. Drug Metabolism and Disposition, 33(9), 1304-1311). | EVA |  | TK_FUB_Riley.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_Votano | Eva | Eva | yes | Votano, J. R., Parham, M., Hall, L. M., Hall, L. H., Kier, L. B., Oloff, S., & Tropsha, A. (2006). QSAR modeling of human serum protein binding with several modeling techniques utilizing structure− information representation. Journal of Medicinal Chemistry, 49(24), 7169-7181. | EVA |  | TK_FUB_Votano.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_cran | Eva | Eva | yes | https://cran.r-project.org/web/packages/httk/index.html | EVA |  | TK_FUB_cran.xlsx | processing method ontox | yes - ONTOX - Eva
TK | FU | TK_FUB_Zhu | Eva | Eva | yes | Zhu, X. W., Sedykh, A., Zhu, H., Liu, S. S., & Tropsha, A. (2013). The use of pseudo-equilibrium constant affords improved QSAR models of human plasma protein binding. Pharmaceutical Research, 30, 1790-1798. | EVA |  | TK_FUB_Zhu.xlsx | processing method ontox | yes - ONTOX - Eva
TK | HLM | TK_HLM_vnnADMET |  |  |  | https://vnnadmet.bhsai.org/vnnadmet/availablemodels.xhtml | TK_HLM_vnnADMET.csv |  |  |  | no - just renamed download file from HLM.csv to TK_HLM_vnnADMET.csv
TK | BSEPinh | TK_BSEPinh_livetox |  |  |  | Montanari_livetox_transporters -files in Data_Sheet_2 - | BSEPINH_training.sdf¦BSEPINH_test.sdf |  |  |  | No
TK | OATP1B1inh | TK_OATP1B1inh_livertox | Eva | Eva | yes | Montanari_livetox_transporters -files in Data_Sheet_2 - | Oatp1b1INH_training.sdf¦Oatp1b1INH_test.sdf |  | Livertox_Oatp1b1INH_all.csv | processing method 3 + standard | No
TK | OATP1B3inh | TK_OATP1B3inh_livertox | Eva | Eva | yes | Montanari_livetox_transporters -files in Data_Sheet_2 - | Oatp1b3INH_training.sdf¦Oatp1b3INH_test.sdf |  | Livertox_Oatp1b3INH_all.csv | processing method 3 + standard | No
TOX | MRDD | TOX_MRDD_DeepPK | Eva | Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | fdamdd_reg_test.csv¦fdamdd_reg_train.csv¦fdamdd_reg_val.csv |  | DeepPK_fdamdd_reg_all.csv | processing method 2 + standard | No
TOX | hERG | TOX_hERG_vnnADMET |  |  |  | https://vnnadmet.bhsai.org/vnnadmet/availablemodels.xhtml | TOX_hERG_vnnADMET.csv |  |  |  | no - just renamed download file from hERG.csv to TOX_hERG_vnnADMET.csv
TK | CYP1A2inh | TK_CYP1A2inh_DeepPK | Enrique | Enrique-Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | cyp1a2_inhibitor_test.csv¦cyp1a2_inhibitor_train.csv¦cyp1a2_inhibitor_val.csv |  | DeepPK_cyp1a2_inhibitor_all.csv | processing method 2 + standard | No
TK | CYP3A4inh | TK_CYP3A4inh_DeepPK | Enrique | Enrique-Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | cyp3a4_inhibitor_test.csv¦cyp3a4_inhibitor_train.csv¦cyp3a4_inhibitor_val.csv |  | DeepPK_cyp3a4_inhibitor_all.csv | processing method 2 + standard | No
TK | CYP2C9inh | TK_CYP2C9inh_DeepPK | Enrique | Enrique-Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | cyp2c9_inhibitor_test.csv¦cyp2c9_inhibitor_train.csv¦cyp2c9_inhibitor_val.csv |  | DeepPK_cyp2c9_inhibitor_all.csv | processing method 2 + standard | No
TK | CYP2C19inh | TK_CYP2C19inh_DeepPK | Enrique | Enrique-Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | cyp2c19_inhibitor_test.csv¦cypc19_inhibitor_train.csv¦cypc19_inhibitor_val.csv |  | DeepPK_cyp2c19_inhibitor_all.csv | processing method 2 + standard | No
TK | CYP2D6inh | TK_CYP2D6inh_DeepPK | Enrique | Enrique-Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | cyp2d6_inhibitor_test.csv¦cyp2d6_inhibitor_train.csv¦cyp2d6_inhibitor_val.csv |  | DeepPK_cyp2d6_inhibitor_all.csv | processing method 2 + standard | No
|  | TOX_Cav12inh_CtoxPred | Carmen | Carmen-Eva |  | https://github.com/issararab/CtoxPred/tree/main/data ; https://pubs.acs.org/doi/10.1021/acs.jcim.3c01301 | data_nav_dev.csv |  | TK_CtoxPred_Cav12inh_firstprocessing.csv | processing method 5 + standard | No
|  | TOX_Cav12inh_ChEMBL | Carmen | Carmen-Eva |  | chEMBL; https://www.ebi.ac.uk/chembl/web_components/explore/activities/STATE_ID:EUZX7nG0ni9El0gGC5wVzQ%3D%3D | Cav_chEMBL_non-curated.csv | /datasets_for_modelling/intermediate_files | TK_ChemBL_Cav12inh_firstprocessing.csv | processing method 4 + standard | No
|  | TOX_Nav15inh_CtoxPred | Carmen | Carmen-Eva |  | hps://github.com/issararab/CtoxPred/tree/main/data ; https://pubs.acs.org/doi/10.1021/acs.jcim.3c01301 | data_cav_dev.csv |  | TK_CtoxPred_Nav15inh_firstprocessing.csv | processing method 5 + standard | No
|  | TOX_Nav15inh_ChEMBL | Carmen | Carmen-Eva |  | ChEMBL; https://www.ebi.ac.uk/chembl/web_components/explore/activities/STATE_ID:C2gom0_SelCrQWdGHcF_uQ%3D%3D | Nav_chEMBL_non_curated.csv | /datasets_for_modelling/intermediate_files | TK_ChemBL_Nav15inh_firstprocessing.csv | processing method 4 + standard | No
|  | TOX_hERGinh_ChEMBL | Carmen | Carmen-Eva |  | chEMBL; https://www.ebi.ac.uk/chembl/web_components/explore/activities/STATE_ID:4kWOcaxnV1Xa-BVRBDtpxw%3D%3D | hERG_chEMBL_non_curated.csv | /datasets_for_modelling/intermediate_files | TK_ChemBL_hERGinh_firstprocessing.csv | processing method 4 + standard | No
|  | TOX_hERGinh_DeepPK | Carmen | Carmen-Eva |  | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data | herg_test.csv¦herg_train.csv¦herg_val.csv |  | DeepPK_herg_all.csv | processing method 2 + standard | No
|  |  | Eva | Carmen-Eva |  | https://vnnadmet.bhsai.org/vnnadmet/availablemodels.xhtml | hERGinh_vnnADMET_original.csv |  | hERGinh_vnnADMET_original.csv | just renamed original downloaded file from hERG.csv to hERGinh_vnnADMET_original.csv | No
|  |  | Eva | Eva | yes | DeepPK - https://biosig.lab.uq.edu.au/deeppk/data
TK | CYP3A4sub | CYP3A4_NO_outliers |  |  |  | ['Zaretzki, J., Rydberg, P., Bergeron, C., Bennett, K. P., Olsen, L., & Breneman, C. M. (2012). RS-Predictor models augmented with SMARTCyp reactivities: Robust metabolic regioselectivity predictions for nine CYP isozymes. Journal of Chemical Information and Modeling, 52(6), 1637. https://doi.org/10.1021/CI300009Z.', 'Manga, N., Duffy, J. C., Rowe, P. H., & Cronin, M. T. D. (2005). Structure-Based Methods for the Prediction of the Dominant P450 Enzyme in Human Drug Biotransformation: Consideration of CYP3A4, CYP2C9, CYP2D6. SAR and QSAR in Environmental Research, 16(1–2), 43–61. https://doi.org/10.1080/10629360412331319871.', 'Tian, S., Djoumbou-Feunang, Y., Greiner, R., & Wishart, D. S. (2018). CypReact: A Software Tool for in Silico Reactant Prediction for Human Cytochrome P450 Enzymes. Journal of Chemical Information and Modeling, 58(6), 1282–1291. https://doi.org/10.1021/ACS.JCIM.8B00035/ASSET/IMAGES/MEDIUM/CI-2018-000356_0013.GIF.', 'de Bruyn Kops, C., Friedrich, N.-O., & Kirchmair, J. (2017). Alignment-Based Prediction of Sites of Metabolism. Journal of Chemical Information and Modeling, 57(6), 1258–1264. https://doi.org/10.1021/acs.jcim.7b00165.', 'Tyzack, J. D., Hunt, P. A., & Segall, M. D. (2016). Predicting Regioselectivity and Lability of Cytochrome P450 Metabolism Using Quantum Mechanical Simulations. Journal of Chemical Information and Modeling, 56(11), 2180–2193. https://doi.org/10.1021/acs.jcim.6b00233.'] | CYP3A4_CYProduct.csv, CYP3A4_CYPstrate.csv, CYP3A4_Metrabase.csv, CYP3A4_Terri.csv, CYP3A4_Deep-PK.csv |  |  | processing method 1 | yes - ProtoADME - Enrique
TK | CYP2C9sub | CYP2C9 |  |  |  | ['Zaretzki, J., Rydberg, P., Bergeron, C., Bennett, K. P., Olsen, L., & Breneman, C. M. (2012). RS-Predictor models augmented with SMARTCyp reactivities: Robust metabolic regioselectivity predictions for nine CYP isozymes. Journal of Chemical Information and Modeling, 52(6), 1637. https://doi.org/10.1021/CI300009Z.','Tyzack, J. D., Hunt, P. A., & Segall, M. D. (2016). Predicting Regioselectivity and Lability of Cytochrome P450 Metabolism Using Quantum Mechanical Simulations. Journal of Chemical Information and Modeling, 56(11), 2180–2193. https://doi.org/10.1021/acs.jcim.6b00233.','Tian, S., Djoumbou-Feunang, Y., Greiner, R., & Wishart, D. S. (2018). CypReact: A Software Tool for in Silico Reactant Prediction for Human Cytochrome P450 Enzymes. Journal of Chemical Information and Modeling, 58(6), 1282–1291. https://doi.org/10.1021/ACS.JCIM.8B00035/ASSET/IMAGES/MEDIUM/CI-2018-000356_0013.GIF.', 'de Bruyn Kops, C., Friedrich, N.-O., & Kirchmair, J. (2017). Alignment-Based Prediction of Sites of Metabolism. Journal of Chemical Information and Modeling, 57(6), 1258–1264. https://doi.org/10.1021/acs.jcim.7b00165.', 'Manga, N., Duffy, J. C., Rowe, P. H., & Cronin, M. T. D. (2005). Structure-Based Methods for the Prediction of the Dominant P450 Enzyme in Human Drug Biotransformation: Consideration of CYP3A4, CYP2C9, CYP2D6. SAR and QSAR in Environmental Research, 16(1–2), 43–61. https://doi.org/10.1080/10629360412331319871.', 'Terfloth, L., Bienfait, B., & Gasteiger, J. (2007). Ligand-Based Models for the Isoform Specificity of Cytochrome P450 3A4, 2D6, and 2C9 Substrates. Journal of Chemical Information and Modeling, 47(4), 1688–1701. https://doi.org/10.1021/ci700010t.', 'Tian, S., Cao, X., Greiner, R., Li, C., Guo, A., & Wishart, D. S. (2021). CyProduct: A Software Tool for Accurately Predicting the Byproducts of Human Cytochrome P450 Metabolism. Journal of Chemical Information and Modeling, 61(6), 3128–3140. https://doi.org/10.1021/acs.jcim.1c00144', 'Myung, Y., de Sá, A. G. C., & Ascher, D. B. (2024). Deep-PK: deep learning for small molecule pharmacokinetic and toxicity prediction. Nucleic Acids Research, 52(W1), W469–W475. https://doi.org/10.1093/nar/gkae254.'] | CYP2C9_CYProduct.csv, CYP2C9_CYPstrate.csv, CYP2C9_Magna.csv, CYP2C9_Terri.csv, CYP2C9_Deep-PK.csv |  |  | processing method 1 | yes - ProtoADME - Enrique
TK | CYP2C19sub | CYP2C19 |  |  |  | ['Zaretzki, J., Rydberg, P., Bergeron, C., Bennett, K. P., Olsen, L., & Breneman, C. M. (2012). RS-Predictor models augmented with SMARTCyp reactivities: Robust metabolic regioselectivity predictions for nine CYP isozymes. Journal of Chemical Information and Modeling, 52(6), 1637. https://doi.org/10.1021/CI300009Z.','Tyzack, J. D., Hunt, P. A., & Segall, M. D. (2016). Predicting Regioselectivity and Lability of Cytochrome P450 Metabolism Using Quantum Mechanical Simulations. Journal of Chemical Information and Modeling, 56(11), 2180–2193. https://doi.org/10.1021/acs.jcim.6b00233.','Tian, S., Djoumbou-Feunang, Y., Greiner, R., & Wishart, D. S. (2018). CypReact: A Software Tool for in Silico Reactant Prediction for Human Cytochrome P450 Enzymes. Journal of Chemical Information and Modeling, 58(6), 1282–1291. https://doi.org/10.1021/ACS.JCIM.8B00035/ASSET/IMAGES/MEDIUM/CI-2018-000356_0013.GIF.', 'de Bruyn Kops, C., Friedrich, N.-O., & Kirchmair, J. (2017). Alignment-Based Prediction of Sites of Metabolism. Journal of Chemical Information and Modeling, 57(6), 1258–1264. https://doi.org/10.1021/acs.jcim.7b00165.', 'Terfloth, L., Bienfait, B., & Gasteiger, J. (2007). Ligand-Based Models for the Isoform Specificity of Cytochrome P450 3A4, 2D6, and 2C9 Substrates. Journal of Chemical Information and Modeling, 47(4), 1688–1701. https://doi.org/10.1021/ci700010t.', 'Tian, S., Cao, X., Greiner, R., Li, C., Guo, A., & Wishart, D. S. (2021). CyProduct: A Software Tool for Accurately Predicting the Byproducts of Human Cytochrome P450 Metabolism. Journal of Chemical Information and Modeling, 61(6), 3128–3140. https://doi.org/10.1021/acs.jcim.1c00144', 'Myung, Y., de Sá, A. G. C., & Ascher, D. B. (2024). Deep-PK: deep learning for small molecule pharmacokinetic and toxicity prediction. Nucleic Acids Research, 52(W1), W469–W475. https://doi.org/10.1093/nar/gkae254.'] | CYP2C19_CYProduct.csv, CYP2C19_CYPstrate.csv, CYP2C19_Metrabase.csv, CYP2C19_Terri.csv, CYP2C19_Deep-PK.csv |  |  | processing method 1 | yes - ProtoADME - Enrique
TK | CYP1A2sub | CYP1A2 |  |  |  | ENRIQUE | ENRIQUE |  |  | processing method 1
TK | CYP2D6sub | CYP2D6 |  |  |  | ENRIQUE | ENRIQUE |  |  | processing method 1

## legend
[*]STATUS | ongoing: dataset original para procesar [step] ongoing: dataset preparado para calcular descriptores ongoing: dataset preparado para calcular descriptores - problemas con algunas moléculas ongoing: calculando descriptores ongoing: descriptores calculados ongoing: finetuning local: developed, but not reimputed local: reimputed in linux server ProtoPRED: already available in ProtoPRED
[**]DESCRIPTORES | [persona] local [pc][SO][all/no3D] [persona] server [wichserver][all/no3D]
[***]processing method | standard | Preprocessing con .../scripts/pre_preprocessed_ONGOING/prepare_preprocessed_and_Hygieia.py output info en corresponding file process_[BATCH]_[date].txt donde BATCH puede ser un modelo conreto o varios Output file .../scripts/pre_preprocessed_ONGOING/results/clean_files/[modelID]_final.csv Procesado para evaluar outliers con script .../scripts/compare_ONGOING/automatization_script_v2.py. Genera tres archivos: all_merged_[modelID].csv con toda la infomación, filtered_final_data_[modelID].csv un archivo un poco más resumido y [modelID].csv, directo para ir a wotan. En este último se han filtrado los outliers ojo, en wotan, se debe ignorar la columna ID_all que queda, pero en este archivo se mantiene para poder hacer un trazado
| processing method 1 + standard | otras bases de datos que no correlacionaban se han eliminado. criterio menos de un 85% de datos en común y ????? descrito en archivo correspondiente en carpeta ../Models/[modelID]/Pasos modelo_[modelID].docx
| processing method 2 + standard | Los datos de train, test y val se juntan con el script ../scripts/DeepPK_IRB.py --> DeepPK_[nombreoriginalarchivo]_all.csv, que se genera en la carpeta input para el proceso standard El archivo resultante es el que va al proceso standard
| processing method ontox + standard | original files were preprocessed by Mirko
| processing method 3 + standard | Los datos de train y test se juntan con el script ../scripts/Livertox_IRB.py --> Livertox_[nombreoriginalarchivo]_all.csv, que se genera en la carpeta input para el proceso standard El archivo resultante es el que va al proceso standard
| processing method 4 + standard | CARMEN explain somewhere searching criteria in pubchem. Original downloaded Pubchem file processed by script ../scripts/filter_data_chEMBL_IRB.py --> generated intermediate file ../datasets_for_modelling/intermediate_files/ only by adding an ID column and custom name, and a final file in ../scripts/pre_preprocessed_ONGOING/input_data/[modelID]_firstprocessing.csv [these tags should be indicated in the arguments]
| processing method 5 + standard | Original downloaded file processed by script ../scripts/filter_data_CtoxPred_IRB.py --> converts values to binary classification and saves final file in ../scripts/pre_preprocessed_ONGOING/input_data/[modelID]_firstprocessing.csv

## propuesta_inicial
Simón
Quiero ver propuesta formal antes del pdf
Estos son los que pedían ellos inicialmente:
clustering estructural
ADME in vitro (caco, metabolismo hepático, CYP)
ADME in vivo (farmacocinetica)
Tox ( por ejemplo MTD?)
Actividad hERG, Nav 1.5 y Cav 1.2
Esta era mi propuesta antes de que enviáramos la propuesta, en la que finalmente no incluimos el desglose de los modelos porque había cierta urgencia:
"Clustering estructural": ¿cómo haríamos esto?
"Adme in vitro (caco, metabolismo hepático, CYP)". Estos modelos, ¿alguno más o alguno no?
Caco-2 permeability
CYP450 1A2 inhibitor
CYP450 3A4 inhibitor
CYP450 2C9 inhibitor
CYP450 2C19 inhibitor
CYP450 2D6 inhibitor
CYP450 1A2 substrate
CYP450 3A4 substrate
CYP450 2C19 substrate
CYP450 2D6 substrate
Human liver microsome (HLM) stability
OATP1B1 inhibitor
OATP1B3 inhibitor
BSEP inhibitor
"ADME in vivo": Estos modelos, ¿alguno más o alguno no?
Bioavailability 20%
Bioavailability 30%
Caco-2 permeability
Human Intestinal Absorption
P-glycoprotein inhibitor
P-glycoprotein substrate
Skin permeability
Blood-brain barrier penetration
Plasma protein binding
Volume of distribution
"Tox (por ejemplo MTD?)". Los modelos de ProtoTOX, ¿no?
"Actividad hERG, Nav 1.5 y Cav 1.2". ¿Tenemos algo?